## Sheet1
Lightning SDK1 To-Do (because I would forget to update a Trello lol)
August 18, 2021 (Updated August 21, 2021)
Feature Description | Type | Completion Status | Completion Date
Fix Gradient Directions that are not left | Bug Fix
Fix calling .NET methods from sandboxed Lua | Bug Fix
Script Co-operation and wait(); | Feature
Physics - Only Stop in one direction on Collision in that direction | Improvement
Event: OnObjectCreated | Feature | Complete | Aug 20, 2021
Event: OnObjectDestroyed | Feature | Complete | Aug 20, 2021
Event: OnWindowSizeChanged | Feature
Event: OnAnimationUpdated | Feature | Complete | Aug 21, 2021
Event: OnAnimationStarted | Feature
Event: OnAnimationStopped | Feature
Event: OnCollisionStart | Feature
Event: OnCollisionEnd | Feature
Event: OnLevelLoaded | Feature
Custom animations | Improvement | Partially? Complete | Aug 21, 2021
Bugfix for nonrelative paths in DDMS | Bug Fix
IGDService (In-Game Debugging Service) | Feature
DebugMode GameSetting (IGDService terminates if not set) | Feature
IGDService Multi-Page Debugging | Feature
BaseException handling added to error messages | Improvement
Do not display messagebox for loading XML if AppName is Polaris | Bug Fix | Complete | Aug 19, 2021 01:25
Instance.GetInheritableClasses() | Feature | Complete | Aug 19, 2021
SCM init - pass Renderer not MaxFPS, MaxFPS in Renderer | Improvement
DDMS Objects know when fully loaded from XML | Improvement
Nested menus | Improvement
Bugfix for service killing | Bug Fix | Complete | Aug 21, 2021
Polaris: Insert Object | Feature
Fix Win32 Dialog File Names (Lightning.Core.NativeInterop.Win32) | Bug Fix
Polaris: Script Editor | Feature
Polaris: Exiting | Feature
Polaris: Property Grid | Feature
Polaris: Explorer | Feature
Polaris: Fix Output | Feature
Polaris: Test Launching | Feature
Polaris: Open | Feature
Polaris: Save | Feature
Polaris: SaveAs | Feature
Polaris: View License | Feature
Polaris: Global Settings Editor (may be pushed back) | Feature
Polaris: TitleBar with current file | Improvement
Welcome Document | External - Documentation
Lua Documentation | External - Documentation